## 2023T1 DiscountMate Project Pla
2023T1 DiscountMate Project Plan
# | TASKS | STATUS | ACTION BY | COMMENTS | STATUS
1 | PROJECT KICKSTART AND HANDOVER STUDY | Not Started |  |  | Not Started
1.1 | - Project Initiation & Team Formation | Not Started |  |  | In Progress
1.2 | - Confirm Team Member Roles | Not Started |  |  | Complete
1.3 | - Review Project Handover Materials | Not Started |  |  | On Hold
1.4 | - Collect and Clarify Trimester 3 Project Requirements | Not Started
1.5 | - Review and Confirm Trimester 3 Product Objectives | Not Started
2 | PLANNING AND DESIGN | Not Started
2.1 | - Create Trello Board for DiscountMate | Not Started
2.2 | - Update Trello Board for DIscountMate Project Tasks and Planning | Not Started
2.3 | - Create Project Plan Draft | Not Started
2.4 | - Review and Update Project Plan | Not Started
2.5 | - Design Data Flow Diagram | Not Started
2.6 | - Design and Update DiscountMate Database Schema | Not Started
2.7 | - Design Machine Learning Approach on Item Price Prediction and Item Recommendation | Not Started
2.8 | - Design Data Visualization Approach (TBC) | Not Started
3 | DEVELOPMENT AND UNIT TEST | Not Started
3.1 | Objective 1: Scripts to perform accurate web-scraping of item information from supermarkets | Not Started
3.1.1 | - Develop Web-Scraping Script for Coles Item Data | Not Started
3.1.2 | - Develop Web-Scraping Script for Woolworths Item Data | Not Started
3.1.3 | - Develop Script for Batch Item Images Download | Not Started
3.1.4 | - Develop Script for Batch Item Images Base64 Encoding | Not Started
3.2 | Objective 2: Scripts for Parsing Obtained Information into Usable Format for Database Entry | Not Started
3.2.1 | - Develop Ingestion, Cleansing and Loading Database Scripts for Coles Data | Not Started
3.2.2 | - Develop Ingestion, Cleansing and Loading Database Scripts for Woolworths Data | Not Started
3.2.3 | - Develop Loading Database Scripts for Item Images | Not Started
3.2.4 | - Setup Weekly Item Data Loading Workflow | Not Started
3.3 | Objective 3: Utilization of Machine Learning for Predicting Item Discount and Provide Item Recommandation to Users | Not Started
3.3.1 | - Collect Historical Item Price Data | Not Started
3.3.2 | - Collect User Shopping Transaction Data | Not Started
3.3.3 | - Develop Ingestion, Transformation and Loading Database Scripts for User Shopping Transaction Data | Not Started
3.3.4 | - Develop ML Model for Unsupervised Learning in Association Tasks | Not Started
3.3.5 | - Develop ML Model for Collaborative filtering Approach | Not Started
3.3.6 | - Develop ML Model for Content-Based Filtering Approach (TBC) | Not Started
3.3.7 | - Train and Review Test Result on Developed Models | Not Started
3.3.8 | - Develop Jobs to Re-train ML Models and Loading Result to Database Weekly | Not Started
3.3.9 | - Develop API for Providing Item Recommendation (TBC) | Not Started
3.4 | Objective 4: Implement OCR for the Scanning of User Receipts | Not Started
3.4.1 | - Develop App Function to Take Image of User Receipt (TBC) | Not Started
3.4.2 | - Develop App Function to Execute OCR Process to the User Receipt | Not Started
3.4.3 | - Develop App Function to Upload the Data of User Receipt to Database After OCR Process | Not Started
3.4.4 | - Update User Interface in Figma for the Scanning User Receipt Function | Not Started
3.4.5 | - Update Database Schema to Store the Data of User Receipt | Not Started
3.4.6 | - Develop Ingestion, Cleansing and Loading Database Scripts for User Receipt Data | Not Started
3.5 | Objective 5: Administrative Management Panel (Manipulate / Update Account / Item Information) | Not Started
3.5.1 | - Develop App Function on Administrative Management Panel to Manipulate / Update Account Information | Not Started
3.5.2 | - Develop App Function on Administrative Management Panel to Manipulate / Update Item Information | Not Started
3.5.3 | - Update User Interface in Figma for the Administrative Management Panel Function | Not Started
3.5.4 | - Update Database Schema According to the Administrative Management Panel Function (TBC) | Not Started
3.6 | Objective 6: Item Categorization and Display / Search Filter | Not Started
3.6.1 | - Develop Item Categorization Filter | Not Started
3.6.2 | - Develop Item Display Filter | Not Started
3.6.3 | - Develop Item Search Filter | Not Started
3.6.4 | - Update User Interface in Figma for the Item Categorization and Display / Search Filter | Not Started
3.6.5 | - Update Database Schema According to the Item Categorization and Display / Search Filter (TBC) | Not Started
3.7 | Objective 7: Cart / Shopping and Favourite Item Lists | Not Started
3.7.1 | - Develop Cart / Shopping List App Function | Not Started
3.7.2 | - Develop Favourite Item List App Function | Not Started
3.7.3 | - Update User Interface in Figma for the Cart / Shopping and Favourite Item Lists | Not Started
3.7.4 | - Update Database Schema According to the Cart / Shopping and Favourite Item Lists | Not Started
4 | TESTING | Not Started
4.1 | - Create Test Cases for User Acceptance Test | Not Started
4.2 | - Deploy Updated Front-end, Back-end, Database and Data Processing Jobs Source Code to the Test Environment | Not Started
4.3 | - Perform User Acceptance Test with the Created Test Cases | Not Started
4.4 | - User Acceptance Test Sign-off | Not Started
5 | DOCUMENTATION & SUBMISSION | Not Started
5.1 | - Update Project Handover Documents | Not Started
5.2 | - Update User Mannuals and Support Documents | Not Started
5.4 | - Update Github | Not Started
5.5 | - Submit Portfolio | Not Started